## Sheet1
Sprint Date | Meeting Location | Attendees | Meeting Notes/Summary | Action Items
2024-10-07 | Discord | Alina Awais Kyle Leander Mikhail Nate | Discussing requirements for Project Part 2, assigning different tasks to each team member | Product Backlog: Leander UI Mockups: Mikhail, Kyle, Awais, Alina CRC Cards: Nate
2024-10-14 | Discord | Alina Awais Kyle Leander Mikhail Nate | Checking in on Project Part 2 requirements | Continue working on assignments
2024-10-18 | Discord | Alina Awais Kyle Leander Mikhail Nate | Discussing the progression of Project Part 3. Everyone chose ~4 stories to work on. Goal for everyone to get at least 2 stories done by the next checkin | See Github milestones for task assignments
2024-10-29 | ETLC | Alina Awais Kyle Leander Mikhail Nate | Check in to see the progress of all team members. Discussed the layout of the Firebase database, and clarified the requirements. | Continue working on assignments. See github milestones for assignments.
2024-11-06 | Lab | Alina Awais Kyle Leander Mikhail Nate | All individual tasks were completed at this point. Working together to merge the code. | Leo volunteered to help with integration, to integrate everyones assignments into the code base.