## Sheet1
Sprint Date | Meeting Location | Attendees | Meeting Notes/Summary | Action Items
2024-10-07 | Discord | Alina Awais Kyle Leander Mikhail Nate | Discussing requirements for Project Part 2, assigning different tasks to each team member | Product Backlog: Leander UI Mockups: Mikhail, Kyle, Awais, Alina CRC Cards: Nate
2024-10-14 | Discord | Alina Awais Kyle Leander Mikhail Nate | Checking in on Project Part 2 requirements | Continue working on assignments
2024-10-18 | Discord | Alina Awais Kyle Leander Mikhail Nate | Discussing the progression of Project Part 3. Everyone chose ~4 stories to work on. Goal for everyone to get at least 2 stories done by the next checkin | See Github milestones for task assignments
2024-10-29 | ETLC | Alina Awais Kyle Leander Mikhail Nate | Check in to see the progress of all team members. Discussed the layout of the Firebase database, and clarified the requirements. | Continue working on assignments. See github milestones for assignments.
2024-11-06 | Lab | Alina Awais Kyle Leander Mikhail Nate | All individual tasks were completed at this point. Working together to merge the code. | Leo volunteered to help with integration, to integrate everyones assignments into the code base.
2024-11-11 | Discord | Alina Awais Kyle Leander Mikhail Nate | Planning which tasks will be assigned to everyone for Project Part 4 | See Github milestones for task assignments
2024-11-18 | Discord | Alina Awais Kyle Leander Mikhail Nate | Check in on progress of part 4. Ensuring everyone knows what tasks they are working on, and that it is working as expected. Prep for the project part 3 demo | Continue working on assignments. See github milestones for assignments.
2024-11-20 | Lab | Alina Awais Kyle Leander Mikhail Nate | Check in before the lab on everyone's progress. Project part 3 demo in lab, and asked any questions for demo. | Continue working on assignments. See github milestones for assignments.
2024-11-25 | Discord | Alina Awais Kyle Leander Mikhail Nate | Check in on everyones progress for part 4. Close to finishing the main functionality of the app, and working on small bug fixes. | Continue working on assignments. Individuals taking on bug fixes related to their initial code, and others helping if needed.
2024-11-27 | Lab | Alina Awais Kyle Leander Mikhail Nate | Discussing any bug fixes we need to work on. Beginning work on test cases, as that was the most difficult part. | Continue working on bug fixes, start working on test cases related to individual user stories.
2024-11-29 | Discord | Alina Awais Kyle Leander Mikhail Nate | Final discussions on work to be done over the weekend. Major assignments are now no longer being modified. Assigning tasks for submission requirements. | Work on tasks related to submission requirements
2024-12-03 | Discord (TODO) | Alina Awais Kyle Leander Mikhail Nate | Discuss how we will do the final app demo during our lab on December 4th | Plan for demo